## Test_Plan
Field | Details
Project Name | OrangeHRM Login Page Manual Testing
Module | Login
Application URL | https://opensource-demo.orangehrmlive.com
Testing Type | Manual Testing
Scope | Login UI, Validation, Database, Session
Out of Scope | Performance, Automation
Test Environment | Windows 10, Chrome
Entry Criteria | Build available, DB accessible
Exit Criteria | All critical defects closed

## Test_Scenarios
Scenario ID | Scenario Description
TS_01 | Verify valid login
TS_02 | Verify invalid login
TS_03 | Verify field validations
TS_04 | Verify UI behavior
TS_05 | Verify session & security

## Test_Cases
Test Case ID | Scenario ID | Test Case Description | Pre-Condition | Test Steps | Test Data | Expected Result | Priority
TC_01 | TS_01 | Valid username & password | User exists | Enter valid creds & login | Admin/admin123 | Login success | High
TC_02 | TS_02 | Invalid password | User exists | Enter wrong password | Admin/wrong | Error message | High
TC_03 | TS_02 | Invalid username | User exists | Enter wrong username | Wrong/admin123 | Error message | High
TC_04 | TS_03 | Empty username | Login page open | Leave username empty | Password only | Validation shown | High
TC_05 | TS_03 | Empty password | Login page open | Leave password empty | Username only | Validation shown | High
TC_06 | TS_03 | Both fields empty | Login page open | Click login | NA | Validation shown | High
TC_07 | TS_03 | Username with spaces | Login page open | Enter username with spaces | Admin | Trimmed | Medium
TC_08 | TS_03 | Password with spaces | Login page open | Enter password with spaces | admin123 | Trimmed | Medium
TC_09 | TS_04 | Password masking | Login page open | Type password | admin123 | Masked | Low
TC_10 | TS_04 | Login button enabled | Login page open | Check login button | NA | Enabled | Low
TC_11 | TS_04 | Tab navigation | Login page open | Use tab key | NA | Correct order | Low
TC_12 | TS_05 | SQL injection | Login page open | Enter SQL | ' OR 1=1 | Login denied | High
TC_13 | TS_05 | Special characters | Login page open | Enter special chars | @@@ | Error | Medium
TC_14 | TS_05 | Multiple failures | User exists | Wrong pwd 5 times | Wrong pwd | Account locked | High
TC_15 | TS_05 | Logout | User logged in | Click logout | NA | Logout success | High
TC_16 | TS_05 | Back after logout | User logged out | Click back | NA | Access denied | High
TC_17 | TS_01 | Case sensitivity | User exists | Uppercase username | ADMIN | Login works | Medium
TC_18 | TS_01 | Remember me | Login page open | Check remember me | Valid creds | Session saved | Medium
TC_19 | TS_05 | Session timeout | User idle | Wait idle | NA | Session expired | High
TC_20 | TS_04 | Error message UI | Invalid login | Observe error | Wrong pwd | Red error msg | Low

## Test_Execution
Test Case ID | Actual Result | Status
TC_01 | As expected | Pass
TC_02 | As expected | Pass
TC_03 | As expected | Pass
TC_04 | As expected | Pass
TC_05 | Issue observed | Fail
TC_06 | As expected | Pass
TC_07 | As expected | Pass
TC_08 | As expected | Pass
TC_09 | As expected | Pass
TC_10 | As expected | Pass
TC_11 | As expected | Pass
TC_12 | Issue observed | Fail
TC_13 | As expected | Pass
TC_14 | Issue observed | Fail
TC_15 | As expected | Pass
TC_16 | As expected | Pass
TC_17 | As expected | Pass
TC_18 | As expected | Pass
TC_19 | As expected | Pass
TC_20 | As expected | Pass

## RTM
Requirement ID | Scenario ID | Test Case ID | Status
REQ_LOGIN_01 | TS_01 | TC_01 | Pass
REQ_LOGIN_02 | TS_02 | TC_02 | Pass
REQ_LOGIN_03 | TS_02 | TC_03 | Pass
REQ_LOGIN_04 | TS_03 | TC_04 | Pass
REQ_LOGIN_05 | TS_03 | TC_05 | Fail
REQ_LOGIN_06 | TS_03 | TC_06 | Pass
REQ_LOGIN_07 | TS_03 | TC_07 | Pass
REQ_LOGIN_08 | TS_03 | TC_08 | Pass
REQ_LOGIN_09 | TS_04 | TC_09 | Pass
REQ_LOGIN_10 | TS_04 | TC_10 | Pass
REQ_LOGIN_11 | TS_04 | TC_11 | Pass
REQ_LOGIN_12 | TS_05 | TC_12 | Fail
REQ_LOGIN_13 | TS_05 | TC_13 | Pass
REQ_LOGIN_14 | TS_05 | TC_14 | Fail
REQ_LOGIN_15 | TS_05 | TC_15 | Pass
REQ_LOGIN_16 | TS_05 | TC_16 | Pass
REQ_LOGIN_17 | TS_01 | TC_17 | Pass
REQ_LOGIN_18 | TS_01 | TC_18 | Pass
REQ_LOGIN_19 | TS_05 | TC_19 | Pass
REQ_LOGIN_20 | TS_04 | TC_20 | Pass

## Bug_Report
Bug ID | Test Case ID | Bug Description | Severity | Status
BUG_01 | TC_05 | No validation for empty password | High | Open
BUG_02 | TC_12 | SQL injection not blocked | High | Open
BUG_03 | TC_14 | Account not locked after failures | High | Open

## DB_Test_Cases
DB Test Case ID | Related Test Case ID | Scenario | UI Action | SQL Query | Expected DB Result | Status
DB_TC_01 | TC_01 | Valid login | Login with valid creds | SELECT last_login FROM users WHERE username='Admin'; | last_login updated | Pass
DB_TC_02 | TC_02 | Invalid login | Wrong password | SELECT last_login FROM users WHERE username='Admin'; | last_login unchanged | Pass
DB_TC_03 | TC_05 | Validation | Empty password | SELECT * FROM login_attempts WHERE username='Admin'; | Failed attempt stored | Fail
DB_TC_04 | TC_12 | Security | SQL injection attempt | SELECT * FROM users; | No data exposed | Fail
DB_TC_05 | TC_15 | Session | Logout | SELECT * FROM user_sessions WHERE logout_time IS NULL; | Session closed | Pass

## SQL_Queries
Purpose | SQL Query
Check user exists | SELECT * FROM users WHERE username='Admin';
Check encrypted password | SELECT password FROM users WHERE username='Admin';
Verify last login | SELECT last_login FROM users WHERE username='Admin';
Failed attempts | SELECT * FROM login_attempts WHERE result='FAILED';
Active session | SELECT * FROM user_sessions WHERE logout_time IS NULL;

## UAT
UAT ID | Business Scenario | Expected Result | Actual Result | Status | Remarks
UAT_01 | Admin login | Dashboard visible | Dashboard visible | Pass | Approved
UAT_02 | Invalid user | Error shown | Error shown | Pass | Approved
UAT_03 | Logout | Session ended | Session active | Fail | Fix required

## Test_Closure
Item | Details
Total Test Cases | 20
Executed | 20
Passed | 17
Failed | 3
Critical Bugs | 1
Test Cycle Status | Completed
Sign-off | Pending after fixes